## Active Projects
Project Name / Number | PM | Notes | Install Onsite Date | Substantial Completion | Control System | Product Supplier | LED Ship Date | Shipping Method | LED on-site | Integration Manager | Integration Sub | Commissioning Date | ANC Commissioning | Structural Engineer | Electrical Engineer | Install Sub | Electrical Sub
Baltimore Ravens | Jesse / JP | Awaiting GA 5/6 install pricing, have sent to Caleb, NST, EST. Concert venue now needs operational by 7/10 | 5/9 - 8/1 | 8/1/2025 (except GA 5/6) | Ross | Nitxeon/LG | En route |  | Mesh: 6/20 Indoor: 6/19 NE Expansion: 6/30 GA5/6: 7/20 Outdoor: 6/24 | Jackson Hart |  | 7/5-7/10 and 8/2 | Tony / Nova | Howard | Peno | EST/Caleb | Malstrom
Boise State Ribbons | Jeff | Install ongoing, Jeff onsite next week | 2026-06-01 | 2026-06-19 | Livesync | LG | Onsite | Ocean |  | Jackson Hart |  |  |  | Howard | Peno | EST | Anderson
Captiol One Arena DP2 and Lofts | David T / Jesse | Reviewed closeout with Krissy, need to pay Tricore to finish a few things. Some seam adjustments also required. | Punch | Punch | WiPro | LG |  | Ocean |  | Jackson Hart
Charlotte Hornets - IPF | Jesse / JP | Trapezoid display size continues to change, coordination ongoing with GC | 2026-10-15 | 2026-01-01 | Livesync/Players? | Nitxeon/LG |  | Ocean |  | Jackson Hart | Baker Audio? | 12/15ish |  | Murdoch | Peno
Charlotte Hornets - OBM | Dagan | Gomez working on contract, need kickoff | [5 empty] | Ocean |  | JW Cooke
Charlotte Hornets - Voms | Dagan | Hobbs working on updating pricing
Heritage Chicago | Dagan | rack build next week | 2026-06-27 | 2026-07-25 | n/a | LG | 2026-04-23 | Air |  |  |  | TBD |  | n/a | n/a | n/a | n/a
Indiana University | Jeff | LED Ordered, OES ordered, onsite coverage needs early July | 2026-08-20 | 2026-09-20 | Livesync | Nitxeon/LG | 2026-06-25 | Ocean | 2026-08-15 | Jackson Hart |  | 9/15ish |  | Howard | Peno | ML | Sun
Indiana Fever | Jeff | Jeff working on submittals | 2027-01-15 |  |  | LG |  |  |  | Jackson Hart |  |  |  | Howard | Peno | ML | Sun
MetLife Stadium | Jesse | Displays complete, electrical inspection outstanding through FIFA | Done | Done | Livesync | LG |  |  |  | Jackson Hart |  | done |  | Murdoch | Peno | EST/Decker | RCR
Nashville SI | Jesse | Hoping for LED Delivery prior to 6/22 | 2026-05-30 | 2026-07-03 | Owner | LG | In transit | Ocean |  | JW Cooke | Baker Audio | 2026-06-29 |  | Howard | Peno | Baker | Baker
Scotia Bank Center (Maple Leafs) - Phase 4 | Jesse / JP | Site Visit Monday, need to get LED ordered ASAP. | 2026-08-01 | 2027-03-01 | Ross | LG |  | Ocean |  | Jackson Hart | RamComm |  |  | Atec | Atec | Atec | Atec/Ramcom
Bilt | Jesse / Nick | Install 8/15, need to send to ITI for pricing. Atrium looking like October. | 8/15 (2nd floor) |  |  | LG |  |  |  | JW Cooke | ITI? | 2026-09-15
Cavs Totem | Jeff | On hold | TBD | 2025-09-01 | Livesync | Nitxeon
Philadephia Union | Jesse/JP | LED Delivery 7/1 | 2026-07-01 | 2026-07-03 | Ross | LG | 2026-06-01 | Ocean | 2026-06-26 | Jackson Hart |  | 2026-06-29 |  | n/a | Peno | EST | Metzger
Rutgers Ribbon | JP | Engineering in progress, need electrical info from client | 2026-07-01 | 2026-08-01 | Livesync | Nitxeon |  |  |  | Jackson Hart |  | 2026-07-29 | Logan | Murdoch | Peno | EST | RCR
Washington Commanders | Jesse / JP | Electrical CO to be submitted to client | 2026-06-01 | 2026-08-01 | Livesync | Nitxeon/LG | 2026-06-01 | Ocean | 2026-07-17 | Jackson Hart |  | 2026-07-29 |  | Howard | Peno | NST | Malstrom
NBC - 9C | Jesse | Kickoff tomorrow, LED ordered | 2026-07-15 | 2026-08-01 | Livesync | LG | In stock | In Stock | 2026-07-15 | Jackson Hart |  | 2026-07-29 | Jackson | Howard | Peno | ITI | ITI
NTM - Union Station | Jesse/ David T | Cameras to be installed Friday , Garage display to be ordered | Now | 2026-05-01 | n/a | Nitxeon | 2026-04-18 | Air |  | JW Cooke |  | done |  | Howard | Peno | ITI | Malstrom
NTM - Sofitel | Alex / ? | Engineering in progress - load study. 4/24 submittal | TBD |  |  | LG |  |  |  | JW Cooke
NTM - Hotel Figueroa | Alex / ? | *Waiting on contact signoff | [7 empty] | JW Cooke
NTM - 939 Sunset | Alex / ? | [8 empty] | JW Cooke
OBM Arsht | Dagan | ON HOLD - City Commissioning meeting in June | [7 empty] | JW Cooke
OBM Legacy Union | Dagan | ON HOLD | [7 empty] | JW Cooke
OBM - San Antonio | Dagan | ON HOLD | [7 empty] | JW Cooke
OBM Sunset Cinema | Dagan | Submittal 6/8, expected formal release early July | 2026-10-05 | 2027-02-26 | TBD | LG | TBD | Ocean | TBD | JW Cooke |  | TBD |  | Howard | Peno | LucentHD | TBD
OBM - Cloud | Dagan | Waiting on official sign off | [7 empty] | JW Cooke
OBM - Blossom | Dagan | Waiting on official sign off | [7 empty] | JW Cooke
OBM - Santa Monica - 301 Arizona | Dagan | Signed off | 2026-07-20 | 2026-08-30 | TBD | Nitxeon/LG | TBD | Ocean | 2026-08-12 | JW Cooke |  | 2026-08-25 |  | Howard | Peno | LucentHD | TBD
OBM - Santa Monica - 1202 3rd St | Dagan | Signed off | 2026-08-15 | 2026-08-30 |  | Nitxeon/LG | TBD | Ocean | 2026-07-28 | JW Cooke |  | 2026-08-25 |  | Howard | Peno | LucentHD | TBD
OBM San Jose | Dagan | Cladding work outstanding once displays are live | Now | 2026-08-12 | n/a | DAK | [5 empty] | n/a
OBM Denver - Home2 | Dagan | Submitted for permitting | 2026-06-08 | 2026-07-06 | TBD | LG | TBD | Ocean | 2026-06-15 | JW Cooke | Pro Media | 2026-07-02 |  | Howard | Peno | LucentHD | LucentE3
OBM - Market St San Jose | Dagan | Awaiting details
Houston Rockets | Jeff | Client meeting 6/24 | [7 empty] | Jackson Hart
Liverpool | Jesse/JP | Coordination ongoing | 7/6 demo/structure 7/23 LED | 2026-08-02 | Ross | Yaham | 2026-06-10 | Train | 2026-07-23 | Jackson Hart |  | 2026-08-01 | Jackson Hart | SSUK | SSUK | SSUK | SSUK
Red Bulls LCD | Jesse/JP | Awaiting site visit to confirm install conditions, awaiting finalized contract
Westfield WTC | Jesse/JP | Electrical and structural engineering in progress. Peno onsite 6/17 | 2026-09-15 | 2027-03-01 | Livesync | Yaham |  |  |  | Jackson Hart |  |  | Ryan Sartell | Howard | Peno
Capitol One Arena | Jesse/JP | LED submittal sent | Fall 2026 |  | WiPro | Yaham | 2026-09-01 | Ocean | 2026-10-01 | Jackson Hart |  |  |  | Howard | Peno
Eagles Marquees | Jesse/JP | Contract signed off, kickoff this week | 2026-07-06 | 2026-08-01 | Livesync? | LG | N/A, at EST Shop |  | currently at EST |  |  | 2026-07-24 |  | EST | EST | EST | RCR
1540 Broadway | Jesse | Kicked off onsite with client this week. Structural engineering in progress | 7/15 (scaffold/demo) | 9/30 (at risk) | TBD | LG | TBD | Ocean |  |  |  | 2026-09-25 | Logan | Scott Lewis | N/A | NSN | NSN
Carolina Panthers |  | Design build for 27/28 - field level display this year
Coca Cola Coliseum | Eric | Supply only to Atec - client needs update on product | [6 empty] | 9/15 to Atec
Closeout / Punchlist
Project Name |  | Notes | Install Onsite Date | Substantial Completion | Control System | Product Supplier
OBM Arlington | Dagan | *Project completed |  | 2025-05-01 | n/a | Translux
OBM Choctaw | Dagan | *Project completed - Mask issue, Eric/Dagan working with INFI/LG | July |  |  | LG
New Tradition Sofitel - Install | Dagan | *Project completed | July |  |  | LG
OBM Brooks Tower | Dagan | *Project completed | 6/9 - 6/13 | 2025-06-02 | n/a | Yaham
Portland Trailblazers | Daniel / JW | Cable drop issue | June/July/August |  | Livesync | Yaham
Orlando Magic | Eric |  | June/July/August |  |  | Yaham
Fifth Third Arena-Chicago Blackhawks | Jeff Jones | Project complete | October/November | 2025-11-01 | n/a | Yaham
DC Metro Convention Center | TBD
Brush Street | Dagan |  | TBD |  |  | LG
49ers | Jesse | 49ers talking with Devcon | June - August | 2025-06-15 | Ross | Nitxeon
DC Metro - Navy Yard | Jesse/ Michael | Project complete
DBH - Gwinnett Stripers | Jeff | Project Complete |  |  | Dak | LG
FDU | Jesse | Shot clocks installed | September / October |  | Livesync | Yaham
LA Dodgers - | Eric | Complete, data cable replacement |  |  | Livesync | LG
Xfinity | Jesse | Complete |  |  | Livesync | Yaham
AT&T Times Square | Alex / Nick | *Awaiting installation of lights. Waiting on cable from LG | September / October |  |  | LG
DBH - New Hampshire Fisher Cats | Jeff | Complete |  | 2026-04-24 | Dak | LG | [7 empty] | Howard | Peno | NST | Oakridge
Florida Panthers | Jack / Jesse | Complete | June/July |  | Ross | Yaham | [7 empty] | Howard | Peno | EST/NST | RCR
Florida Panthers Marquee's | Jack / Jesse | Complete |  |  | Ross | Yaham | [7 empty] | Howard | Peno | NST | RCR

## Closeout (hidden)
Project Name | Start | Finish | Onsite Start | Onsite Finish | Resource Names | Phase | Notes | Punchlist | Training | Closeout Docs | Signoff | Product Issues | Final Payment Invoiced | Final Payment Rec'd
270 Park - East Side Access | Sat 1/15/22 | Tue 2/15/22 |  |  | Jesse | closeout | Spare parts quote from Digi (invoice Tishman directly) - Paid in full | Module swap | x | x |  |  | x | x
Cal Berkeley Football | Mon 5/2/22 | Fri 8/5/22 |  |  | Andrew,Blayne | closeout | Trim to be installed tomorrow, this weekend | EST onsite to finish trim |  | BC/KC - meet/review |  |  | x
Columbia U | Mon 8/1/22 | Sat 10/1/22 |  |  | Daniel,Jesse | closeout | OES instaled, being wired this week | OES delievery to install clock-December | x | x
Fenway Park | Fri 10/8/21 | Fri 4/15/22 |  |  | Daniel | closeout | Malik working with Michael to close this out to receive payment
TIN Building Round 2 | Sun 2/20/22 | Wed 3/23/22 |  |  | Jesse | closeout | Malik, waiting on feedback from client |  | x | x |  |  | x
Vanderbilt | Mon 9/27/21 | 2022-11-06 |  |  | Daniel,Jeff | closeout | Pixel damage, corner mesh move/replace | EST finalizing mesh 11/4
Crowley ISD | Fri 10/15/21 | 2022-11-10 | 44866 | 44875 | Daniel,Blayne | closeout | Blayne / Felipe working on punchlist | Pixel issues in progress
Westgate | Fri 10/15/21 | Fri 7/15/22 |  |  | Malik | Pre-construction | CO for ladder sent to AJP - Call Kirsten
Royal Caribbean | Mon 8/22/22 | 2022-11-15 |  |  | Andrew | Closeout | Pixel repairs, time for Tommy onsite for repairs. Finalize CO's with client.
Ohio State Field Hockey | Mon 3/21/22 | Mon 8/1/22 |  |  | Daniel | Onsite | Need payment
Indiana Pacers | Sun 8/15/21 | Sun 11/6/22 |  |  | Jeff | onsite | JJ-Punchlist issued / Digi issue w/seams |  | Jeff Jones f/u on walk thru
Ohio State Lacrosse |  |  |  |  | Daniel |  |  | Outstanding: test all OES/virtual scoring and install netting
Omni PGA Frisco Resort | 2022-10-24 |  |  |  | Jessie | Complete |  | Wrapping up next week, internet done this week. Felipe onsite next week.
LA Dodgers Stadium Club |  |  |  |  | Daniel/Jackson |  |  |  |  | Install 1/11/2023
U of Pittsburg | 2023-01-30 |  | 2023-03-01 |  | Jesse | [6 empty] | final walk pending

## Complete (hidden)
Project Name | Start | Finish | Onsite Start | Onsite Finish | Resource Names | Phase | Notes
Cal Berkeley Softball | Mon 5/9/22 | Fri 5/13/22 |  |  | Andrew,Blayne | complete
Chicago Renaissance Hotel | Fri 11/12/21 | Wed 6/15/22 |  |  | Daniel,Jeff | complete
Louisville Football Ribbons | Fri 9/17/21 | Wed 10/6/21 |  |  | Jeff | complete | complete
University of Louisville Angels Envy | Mon 7/4/22 | Sun 8/7/22 |  |  | Jeff | complete | rec'd final payment 10/21/2022
University of Louisville Field Hockey | Mon 8/9/21 | Fri 10/15/21 |  |  | Jeff | complete
University of Louisville Lacrosse | Mon 11/1/21 | Fri 12/24/21 |  |  | Jeff | complete
Western Kentucky | Fri 7/29/22 | Fri 8/26/22 |  |  | Daniel | complete | complete
Temple IPTV | Mon 8/16/21 | 2022-12-01 |  |  | Jesse,Jackson | Closeout | Bill in full | Bill in full
Moynihan Mount Replacement | 2022-12-01 | 2022-12-31 |  |  |  |  | Daniel overnight work - 12/18
Phillies - IPTV | Sun 3/13/22 | TBD |  |  | Jackson | Pre-construction | Expanding-ordering more
College of Charleston | Sun 2/27/22 | Sun 7/10/22 |  |  | Jesse | closeout | Waiting on final payment | x | x | x | x | x
Brick and Bev - Armory | Thu 9/1/22 | 2022-11-07 | 2022-11-01 | 2022-11-15 | Jeff | Onsite | Completeing closeout docs - repaired mods back onsite
NBC | Sat 10/1/22 | 2023-01-09 |  |  | Daniel | Onsite | As built and closeout done
Westgate |  |  |  | Jeff | [8 empty] | CO for ladder sent to AJP - Call Kirsten
TIN Building Round 2 |  |  |  | Eric | [7 empty] | x | Malik, waiting on feedback from client
LA Dodgers Stadium Club |  |  |  | Jackson | [8 empty] | Waiting on Analog Way Payment for completion

## On-Site PM Schedule (JOE)
| Revenue | Margin | IC Cost |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
Project |  |  |  | Integration | Integration Onsite | Week #1 | Week #2 | Week #3 | Week #4 | Week #1 | Week #2 | Week #3 | Week #4 | Week #1 | Week #2 | Week #3 | Week #4 | Week #1 | Week #2 | Week #3 | Week #4 | Week #1 | Week #2 | Week #3 | Week #4 | Week #1 | Week #2 | Week #3 | Week #4 | Week #1 | Week #2 | Week #3 | Week #4 | Week #1 | Week #2 | Week #3 | Week #4 | Week #1 | Week #2 | Week #3 | Week #4 | Week #1 | Week #2 | Week #3 | Week #4 | Week #1 | Week #2 | Week #3 | Week #4
Baltimore Ravens NW Plaza, Ticket Windows, Ribbons, TVs | 5101000 | 719000 |  | Ross |  | April Week #1: Jesse / ?
Boise State Endzone Ribbons | 677795.64 | 135559.13 |  | Livesync |  | March Week #3: Jeff / Jeff
Captiol One Arena DP6 Project | 10000000 | 1000000 |  | Visibowl Cameras |  | June Week #1: Jesse / JP
Charlotte Hornets - IPF | 1231663 | 187206 |  | Livesync |  | October Week #1: Jesse / ?
DBH - Gwinnett Stripers | 500000 | 50000 |  | Livesync |  | March Week #1: Jeff / Jeff
DBH - New Hampshire Fisher Cats | 350000 | 50000 |  | other |  | March Week #1: Jeff / Tony (FT Boston)
DC Metro |  |  |  | Livesync |  | March Week #1: Daniel / Ops?
Indiana University | 586000 | 103000 |  | Livesync |  | July Week #1: Jeff / Jeff
LA Dodgers - | 6000000 | 1041000 | 55000 | Livesync |  | February Week #1: Eric / JW
MetLife Stadium | 5717000 | 775000 |  | Livesync |  | February Week #1: Jesse / Jesse
Nashville - SI | 704000 | 101000 | 25000 | other |  | April Week #4: Jesse/JW
Boise State -- West Fascia Ribbon Relocation and New East Ribbon | 749000 | 126000 |  | Livesync |  | June Week #1: Jeff/Jeff/Ben Adams?
Philadelphia Union - Pitch Side | 826000 | 148000 |  | Ross |  | May Week #2: Jesse/Dennis
Houston Rockets - LG Technology Refresh | 2425000 | 372000 |  | Ross |  | June Week #1: Jesse / Ben Adams? / JW?
MLSE - Scotiabank Arena - Phase 4 - 2026 Upgrades | 3800000 | 980000 |  | other | bar: June Week #1 to September Week #1
CocaCola | 500000 | 50000
Temple University | 600000 | 120000
Rutgers | 750000 | 150000 |  |  |  | June Week #1: Jesse / Nick / PT
Wahington Commanders | 1500000 | 250000 |  |  |  | June Week #1: Jesse / Michael Lewis?
University of Maine - New Campus (Morse Arena) | 2500000 | 250000 |  | Livesync |  | November Week #1: Jeff /
Indiana Fever -- Sports Performance Center | 1990000 | 300000
NBCU - 9C Project at 30 Rockefeller Center | 1100000 | 325000 |  | Livesync | bar: August Week #1 to August Week #4
Wells Fargo Center Club Level Displays | ? | ? |  | Livesync | bar: August Week #1 to August Week #4
Philadelphia Eagles - Marquees ? | ? | ? | bar: May Week #4 to June Week #3
World Trade Center | ? | ? | ?
| 47607458.64 | 7232765.13 | 80000
ATT LG NYC |  |  |  | other |  | February Week #1: Jesse / Nick (FT NYC)
BILT - NYC HQ (837 Washington Street) Atrium Screen LED ONLY |  |  |  | other |  | April Week #1: Jesse / Nick (FT NYC)
OBM Projects | 24316265 | 2718374 | 0
OBM - 51 Brookline | 1919210 | 336629 |  | other |  | February Week #1: Dagan / Degan / Tony (FT Boston)
OBM - Adrieene Arsht Center Digital Spectacular West (Miami) | 7011694 | 732884 |  | other
OBM - Adrienne Arsht Center Digital Spectacular East (Miami) | 8867830 | 801488 |  | other
OBM - San Jose McEnery CC R1 | 2218604 | 228845 |  | other |  | March Week #1: Dagan / Dagan
OBM - San Jose - 2nd and San Carlos | 630901 | 87092 |  | other |  | February Week #1: Dagan / Dagan
OBM - Denver - Home 2 Suites | 757321 | 110407 |  | other |  | March Week #1: Dagan / Dagan / Commissioning 6/30
OBM - Denver - Aloft | 738607 | 107437 |  | other
OBM - Santa Monica 1 | 1146340 | 165438 |  | other |  | April Week #3: Dagan / Commissioning 7/20; September Week #3: Dagan / Dagan
OBM - Santa Monica 2 | 1025758 | 148154 |  | other |  | April Week #3: Dagan / Commissioning 7/20; September Week #3: Dagan / Dagan
OBM - Sunset Cinema - Phase 2 (2027) | 3849526 | 410091 |  | other |  | July Week #4: Dagan / Commissioning 11/9
OBM - San Jose Market and San Jose (2027) | 689947 | 84815 |  | other
OBM - Los Angeles Cloud (2007) | 3844237 | 151068 |  | other
NTM and Heratage Projects | 16451512 | 2810698 | 125000
Heritage - Chicago OOH (Open to Buy) | 250000 | 70000 |  | other |  | March Week #3: Supply Only
NTM - Union Station | 3000000 | 500000 | 70000 | other |  | April Week #1: David / Pat
NTM - Los Angeles - Sofitel P3/4 | 1138815 | 257700 | 55000 | other |  | September Week #3: Dagan / Dagan
NTM - Sunset 1 | 2100000 | 350000 |  | other
NTM - Los Angeles Hotel Figueroa (2027) | 7862697 | 1282998 |  | other
NTM - Sunset 2 (2027) | 2100000 | 350000 |  | other | bar: March Week #1
KSP - Portfolio RFP
Galveston Terminal Pier 16 - Hensel Phelps - 2025 Additional Displays |  |  |  | Livesync
Cleveland Cavaliers - LED Totem - AJP RFP | 1480000 | 159354 |  | Livesync
Philadelphia Eagles - Full Scope |  |  |  | Ross

## March 23 (hidden)
2023-03-01
| 26 | 27 | 28 | 1 | 2 | 3 | 4
| 5 | 6 | 7 | 8 | 9 | 10 | 11
| 12 | 13 | 14 | 15 | 16 | 17 | 18
| 19 | 20 | 21 | 22 | 23 | 24 | 25
| 26 | 27 | 28 | 29 | 30 | 31 | 1

## Old Projects
Done: Paid and Closed Out
| Portland Timbers |  | Yes | No, Daniel | 2023-07-05 |  | 2023-07-11 | None | Lighthouse
| Texas Tech Underbelly | [7 empty] | Lighthouse
| Rutgers Football |  | No | No | 2023-02-02 |  | 2023-04-14 | Livesync | Lighthouse
| Vanderbilt Module Replacement | [7 empty] | Lighthouse
| College of Charleston Baseball |  |  |  | 2023-11-06 | Felipe |  | Livesync | Lighthouse | On-Site
| U of Alabama, Football | [5 empty] | 2023-08-15 | None | Lighthouse
| Prudential Center | [7 empty] | Lighthouse
| PSU Football Practice | [6 empty] | Livesync | SNA Install
| Ole Miss Team Room | [7 empty] | Planar
| Ohio State Lacrosse | [7 empty] | Lighthouse
| Rutgers Baseball/Softball/Soccer | [5 empty] | 2023-03-03 | Livesync | Lighthouse
| SMU Football North End Zone |  | No | In Progress |  | Jesse | 2023-09-01 | Livesync | Lighthouse
| Crowley ISD |  | Yes | Yes |  | Renaldo |  |  | Lighthouse
| University of Rhode Island |  |  | In Progress |  | Paul |  |  | Lighthouse
| LN-Ameris - Atlanta |  |  |  | 2023-04-30 |  | 2023-04-26 | Diversified | DigiLED
| Fulton ReFresh |  |  |  | 2023-12-12 | DM | 2023-12-15 | LiveSync | Lighthouse | Installed
| Washington Commanders Football | [5 empty] | 2023-06-14 | Ross/DAK by Others | Lighthouse
| BMO Harris |  | No | Yes |  | Daniel/Jeff | 2023-06-16 |  | Lighthouse
| Iona Prep |  |  |  | 2023-01-08 | JJ | 2024-02-01 | LiveSync | Lighthouse | LED in production
| Arkansas South Scoreboard and Ribbons |  | No | In Progress |  | Daniel/Jeff | 2023-08-15 | Livesync | Lighthouse
| Portland Trailblazers Voms |  |  |  | Currently Ongoing | Taylor Nebeker |  | LiveSync | Lighthouse | Installed
| Superdome Capital Improvements - Phase 2 (NEED FINAL PAYMENT) | [7 empty] | Lighthouse
| Texas Motor Speedway |  |  |  |  | Daniel | 2023-09-25 | None | DigiLED
| USC, Hall of Fame |  |  |  |  | Jack |  |  | Planar
| Marshall University - Softball | closeout docs sent to client 4.15.24 |  |  | Currently Ongoing | DM | 2024-03-01 | Livesync | Lighthouse
| Marshall University - Baseball | closeout docs sent to client 4.15.24 |  |  | Currently Ongoing | DM | 2024-03-01 | Livesync | Lighthouse
| Marshall University - Football | closeout docs sent to client 4.15.24 |  |  |  | Daniel | 2023-11-25 | Livesync | Lighthouse
| Tishomingo Center AV | Closeout docs sent to client 4.26.24 |  |  |  | Jackson | 2022-11-12
| Melissa ISD Football | Closeout docs sent to client 4.26.24 |  |  |  | Renaldo | 2023-05-15 | Livesync | Lighthouse
| Alabama Baseball and Softball | Closeout docs sent to client 4.26.24 |  |  | 2024-03-01 | JJ | 2024-03-05 | Dak | Lighthouse
| USC Tennis | closeout package ready to send 4.15.24 - on file when needed |  |  |  | Jack | 2023-08-01 | Livesync | Lighthouse
| Mets Home Plate | closeout package ready to send 4.15.24 - on file when needed |  |  | 2024-02-01 | JJ | 2023-01-31 | LiveSync | Lighthouse
| Arkansas Home Plate | training; rack drawings (if applicable) |  |  | 2024-03-01 | JJ | 2024-03-04 | Dak | Lighthouse
| ATL Airport-Hartsfield-Jackson Domestic Terminal | closeout package ready to send 4.26.24 - on file when needed |  |  | 2024-06-15 | DM | 2024-07-01 | n/a | Esprit
| Prudential Center | Closeout/Punchlist; rack drawings (if applicable) |  |  | 2024-03-11 | DM | 2024-03-19 | Click | Lighthouse
| Penn State Baseball | closeout sent 6/18/24 |  |  | Currently Ongoing | JM | 2024-03-15 | LiveSync | Lighthouse
| Cal Berkely | LED installed and operational |  | Installed | complete | Jack | 2024-06-21 | Livesync | Lighthouse
| Washington Nationals |  |  |  | Currently Ongoing | JV | 2023-03-15 | Ross | Lighthouse
| Brewers CF/RF Scoreboard | Closeout/Punchlist |  |  | Currently Ongoing | JV | 2023-03-15 | Ross | Samsung
| Wells Fargo Center Outdoor |  |  |  | Currently Ongoing | JV | 2024-04-01 | Livesync | Lighthouse
| Arkansas Soccer |  | 2024-07-15 | 2024-07-15 | Jeff/Jack | 2024-07-20 | Dak | Lighthouse
| U of Maine Hockey | closeout sent 7.29.24 |  |  | Jeff | 2023-09-01 | Livesync | Lighthouse
| Cross Insurance Arena | Install 7/29 | Onsite | 2024-07-29 | Jeff | 2024-07-29 | Livesync | Lighthouse
| Javits Center | LED install ongoing, waiting to test 7/29 or 7/30 | Onsite |  | Daniel | 2024-07-30 | Brightsign | Lighthouse
| Marshall University - Soccer | LED up and running | Onsite | 2024-06-10 | Renaldo | 2024-07-17 | Livesync | Lighthouse
| Perth | Chris D onsite for install
| Amica Mutual Pavilion | Waiting closeout and final inspection by state | Onsite | TBD | Jeff | 2024-07-24 | Livesync | Lighthouse
| Baylor Arena | Courtside issues, final OES testing womens court, XLR plate install | Installed |  | Renaldo | 2024-07-01 | Ross | Lighthouse
| West Virginia Football | closeout docs | Installed | Installed | Renaldo | 2024-06-01 | Chyron | Lighthouse
| NBC Peacock Lounge and Team Store | Punchlist/closeout | installed | 2024-08-24 | Daniel | 2024-09-01 | Livesync | Planar
| SMU Field Level | LED testing to be done today; closeout docs sent 10/9/24 | In Argyle | 2024-09-07 | Dagan | 2024-09-26 | Ross | Lighthouse
| SMU South Endzone | closeout docs sent 9/18/24 | Onsite | Installed | Dagan | 2024-09-01 | Ross | Lighthouse
| OSU-Reser Stadium | Daniel working with Joe on this. |  |  | Daniel | 2023-08-15 |  | Lighthouse
| Commanders | closeout docs | 2024-08-05 | 2024-08-01 | Jesse | 2024-08-15 | Ross | Lighthouse
| Toyota Center Voms Marquee, End Zone, Ribbons, and CH | closeout, final punch 9/26 |  |  | Daniel/Renaldo | 2024-09-15 | Ross | Lighthouse
| Toyota Center, Hockey Voms | Ex-fac 9/30 | Ex-fac 9/30 |  | Renaldo | 2024-09-15 | Ross | Lighthouse
| Arizona Athlietci Grounds | LED installed, waiting on fiber. | Onsite | ongoing | Jeff | 2024-11-30 | Livesync | Lighthouse
| Toyota Center, CH | Control Room | Installed | 2024-06-25 | Renaldo | 2023-09-01 | Ross | Lighthouse
| Charlotte Motor Speedway | Waiting punchlist walk with GoVision | Onsite | complete | Ethan | 2024-10-07 | n/a | Digi
| Joe Gibbs Racing | Ex-fac 11/30, supply only | 2024-12-08 |  | Daniel | 2024-12-01 | Livesync | Yaham
| American Airlines Center Hung | Final Closeout/cleanup items. Pixel repair, color calibration, final backup testing Trash or keep Samsung CH Product 11.1 - Closeout package emailed to client | Installed | 2024-07-15 | Dagan | 2024-09-01 | Dak | Lighthouse
| American Airlines Center Locker Room | LED install complete | 2024-10-09 |  | Dagan | 2024-10-22 | Dak | LG
| Smoothie King Center Voms and Marquee | Closeout, waiting final punchlist from Eileen |  |  | Daniel/Jeff | 2023-10-29 |  | Lighthouse
| Smoothie King Center Ribbons | waiting laptop to arrive. | Onsite | Installed | Jeff | 2024-07-10 | Chyron | Lighthouse
| La Salle |  | Installed | complete | Jack/Jesse | 2024-10-15 | Livesync | Lighthouse
| Wyoming |  |  |  | Jeff | 2025-04-01 | Dak | LG
| Toyota Center | Chris D and Nova onsite 1/10 and 1/11
| SKC | Nova remote troubleshooting 1/2 and onsite 1/27 pending remote support
| Prudential Center | Dane onsite 1/6 to troubleshoot HDMI extenders
| Select Financials | Felipe onsite 12/30 and 12/31 | Installed |  | Renaldo | n/a | Livesync | Lighthouse
| Prudetnail Center | rack, velcro, PC, for foundry bar
| Xavier Courtside | *Shipping 1/29/25 | Ex-fac: 1/29 |  | Daniel |  | n/a
| PPG Arena | Closeout, waiting on Invetory | Installed | 2025-01-06 | Daniel
| Pacers 360 Ribbon and Endzones | Power control and trim installed as of week 1/27 | TBD | 2024-07-13 | Jeff | 2024-08-24 | Livesync | Lighthouse
| Baylor | Stanchion install 2/5
| WVU | Padding adjustments
| Toyota Center | Foggers to stay or be removed so we can closeout project 2.7.25 - closeout file complete & ready for distribution - KGS | Installed
| JetBlue | *LED testing next week, LED Installed | Installed | Ongoing | Jesse |  | Livesync
| Detroit Tigers HP | *LED install 3/30 | Ex-fac: 3/1 | 2025-03-10 | Jeff | 2025-04-01 | n/a
| LA Dodgers Locker Room and Meeting Ops | *Install ongoing | Ex-fac: 2/20 | 2025-03-01 | Jeff | 2025-03-15 | Livesync
| LA Dodgers HP | *Spare Parts | Ex-fac: 3/1 | 2025-03-10 | Jeff | 2025-04-01 | Livesync
| Diamod Desert Arena | Daniel | *On hold pending CO signoff *Tentative Date 4/21 install (EST+Ethan)
107829 | Portland Sea Dogs |  | *Closeout - compiled & sent to PM for final review 5.6.25 | Ex-fac 2/20 | 2/20? | Jack |  | Livesync
| Tacoma Rainers |  |  |  |  | 2025-02-21
| Brooklyn Cyclones |  | *Waiting Punchwalk with AJP + closeout | Onsite | Ongoing | 2025-04-01 | Livesync
| Fenway Park |  | *LED install complete - closeout docs | Main Video Onsite: 2/8 | Ongoing | 2025-04-01 | Livesync | LG
| Oregon State |  | Power Control
| Cavs Signage | Daniel / Eric | *Finals letters done this week? |  |  | 2025-05-15
| US Squash | Jack
| New Tradition Children's Museum | Daniel |  | Ex-fac: 2/20 | 3/10? |  | n/a
| Capitol One Arena (Monumental, COAT) | Renaldo |  | Arrived in Argyle | 2025-03-20 | 2025-05-01 | Brightsign
| Baltimore Ravens - Practice Facility TVs | Jesse | *TVs onsite. Working through ceiling mount detials / drawings with WT | LCD's onsite | July |  |  | LG
| UMASS Lowell - CMS | Jackson | *Kickoff required 5/2 |  |  |  |  | n/a
| Detroit Tigers | Jeff Jones | *LED onsite 9/22 - waiting shipping date for Lexan
| 1604 Broadway | Daniel / Jackson | *Pixel Repairs |  |  |  | 2/15? |  | n/a | Yaham
| New Tradition Chicago |  | *Project on hold. |  |  | At Lucent |  | n/a | n/a | Translux
AAC
| Baylor |  | *Final Pucnchist items complete and permits closed.
| Scotia Bank Center (Maple Leafs) - PH2 | Daniel | *punchlist complete |  |  | Install ongoing | Ongoing | 2025-03-01 | n/a | LG
| Winston Salem | Jeff Jones | *closeout sent
106963 | Noblesville Grand Hall | Jeff Jones | *closeout docs sent |  |  |  | 2025-03-15 | 2025-06-01 | Livesync | LG
107523 | OBM LA NOW | Dagan | *Punch List Walk 4/25 |  |  | LED at Lucent's shop | 2/15? | 2025-03-15 | n/a | Yaham
106963 | Noblesville CH | Jeff Jones | *Pylon final outstanding item |  |  | LED installed |  | 2025-06-01 | Livesync | Yaham
| St Bonaventure | TBD | *Stanchion Installation - 10/22
| Galvesten Cruise Terminal 16 | Jack | *closeout compiled and waiting on rack drawings - KGS | LED onsite early July | July | 2025-08-01 | Livesync
| Capitol One Courtside | Daniel / David T | *Need to review with DT
107074 | Alfond Arena OES and Ribbon | Jeff Jones | closeout sent 11.26.25 | Arrived in Argyle | July | 2025-08-01 | Livesync | Yaham
| Fulton | Daniel | *closeout ready to be sent
| Prudential Center Ribbons |  | closeout sent 11.26.25
107246 | Fifth Third Ballpark | Jesse | *closeout sent | Installed | Ongoing | 2025-04-15 | Livesync | Yaham
107790 | Golden Park (synones park) | Renaldo | *closeout sent | LED Onsite: 2/3 | 2025-02-03 | 2025-03-15 | Livesync | Yaham
| Cavs Media Wall | Jeff Jones | *closeout sent
| Aventura Mall | Jackson | *12/8/25 integration onsite |  | 2025-02-01 | Livesync | Esprit
| Washington Commanders LED and LiveSync | Jesse | *closeout | July |  | Livesync | Yaham
| Wells Fagro Center Billboard | Jesse | *closeout | August |  |  | LG
LIVE NATION
| LN Ph. 5-Jiffy Lube Live - DC | Moving to Jiffy Lube Live | [5 empty] | Diversified | DigiLED
| LN Ph. 5-PNC - NJ | Moving venues |  |  |  |  | 2023-06-03 | N/A | DigiLED
| LN Ph. 5-xFinity Theater Hartford - Conn | Ted working on drawing updates |  |  |  |  | 2023-06-01 | N/A | DigiLED
| LN Ph. 5-Jiffy Lube Live - DC | One more permitting step, event 1 april 1. |  |  |  |  | 2023-05-06 | N/A | DigiLED
| Ak-Chin Roadside Marquee - Phoenix | Supply only | [5 empty] | N/A | DigiLED
| Ak-Chin Pavillion Marquee (2021) - Phoenix | Screen moving | [5 empty] | N/A | DigiLED
| Ithink - West Palm | No updates or dates - drawings complete. |  |  |  |  | 2023-04-29 | N/A | DigiLED
MISC
| Catalyst (supply only) | Mt Laurel shipment first, Flemmington after - supply only | [6 empty] | Lighthouse
| Legacy Sports | Client filed for bankrupcy | [6 empty] | Lighthouse

## Sheet1
Stage ? |  | Account Name | Opportunity Name | Award Date | Estimated Start | Estimated Completion | Technology Vendor/Partner | Substantial Completion Date
Prospecting |  | Camping World Stadium (Orlando) | Camping World - 2026 LED Upgrade RFP | 2026-04-01 | 2026-04-01 |  | LG Electronics | 2027-01-01
|  | Carolina Panthers | Carolina Panthers - BofA Stadium Upgrades | 2026-07-01 | 2026-07-01 |  | LG Electronics | 2028-05-01
|  | Moody Center | Moody Center / OVG - New LED Wall Locations | 2026-04-01 | 2026-06-01 |  | LG Electronics | 2026-09-01
|  | Rose Bowl | Rose Bowl --South Endzone LED Renovation - AJP RFP | 2026-03-01 | 2026-07-01 |  | LG Electronics | 2026-09-01
Subtotal | Sum
| Count | 4
Evaluating |  | Baltimore Ravens ¦ M&T Bank Stadium | Baltimore Ravens - 2026 LED Ribbon Board Replacement | 2026-02-01 | 2026-03-01 |  | LG Electronics | 2026-08-01
|  | Baltimore Ravens ¦ M&T Bank Stadium | Baltimore Ravens - Ticket Windows on Russell Street - LED Upgrade | 2026-02-01 | 2026-03-01 |  | LG Electronics | 2026-08-01
|  | Carolina Panthers | Carolina Panthers - Practice Facility Upgrade | 2026-06-01 | 2026-08-01 |  | LG Electronics | 2026-12-31
|  | Charlotte Hornets ¦ Spectrum Center | Charlotte Hornets - Spectrum Center Upgrades | 2026-05-01 | 2026-06-01 |  | LG Electronics | 2026-09-30
|  | DC United (MLS) / Audi Field | DC United - 2026 Audi Field Upgrade | 2026-09-30 | 2026-11-01 |  | LG Electronics | 2027-02-01
|  | Monumental Sports & Entertainment (MSE) | COAT - Façade (DP6) Project | 2026-03-01 | 2026-05-01 |  | LG Electronics | 2026-09-01
|  | Monumental Sports & Entertainment (MSE) | Monumental Sports - Capital One Arena - Lexus Garage Display | 2026-03-01 |  |  | LG Electronics | 2026-11-15
|  | NBC Universal | NBCU/30Rock - Today Show Plaza | 2026-07-01 | 2026-08-01 |  | LG Electronics | 2026-12-31
|  | Portland Trail Blazers ¦ Moda Center | Portland Veterans Memorial Coliseum - AJP RFP | 2026-01-06 |  |  | Nitxeon | 2026-08-15
|  | Rutgers University | Rutgers -- Endzone Ribbons | 2026-01-30 | 2026-05-01 | 2026-08-15 | Nitxeon | 2026-08-10
|  | Temple University | Temple -- McGonigle and TSC LED Refresh | 2026-03-01 | 2026-05-01 | 2026-08-15 | Nitxeon | 2026-08-03
|  | University of Louisville | Louisville - Swimming | 2026-04-01 |  |  | Nitxeon | 2026-10-01
|  | University of Louisville | Louisville -- Volleyball LED Screen | 2026-01-30 | 2026-05-01 | 2026-08-01 | Nitxeon | 2026-08-03
|  | Washington Commanders | Washington Commanders (SOW #TBD) - 2026 Projects | 2026-03-11 |  |  | LG Electronics | 2026-08-01
Subtotal | Sum |  |  |  | 2026-03-01
| Count | 14
Negotiation |  |  |  | 2026-07-07 | 2026-03-01 |  | LG Electronics | 2026-09-01
|  |  |  | 2026-04-01 | 2026-06-01 | 2026-08-15 | Nitxeon | 2026-09-01
|  |  |  | 2026-05-01 | 2026-10-01 |  | LG Electronics | 2027-01-01
|  |  |  | 2026-04-01 | 2026-07-01 | 2026-01-31 | LG Electronics | 2026-12-31
|  |  |  | 2026-03-06 | 2026-04-01 | 2026-09-15 | LG Electronics | 2026-08-30
|  |  |  | 2026-03-01 | 2026-04-01 |  | LG Electronics | 2026-09-01
|  |  |  | 2026-02-13 | 2026-05-01 | 2026-11-30 | LG Electronics | 2026-12-31
|  |  |  | 2026-02-16 | 2026-02-16 | 2026-12-31 | LG Electronics | 2027-02-01
|  |  |  | 2026-02-01 | 2026-01-15 |  | LG Electronics | 2026-02-16
|  |  |  | 2026-02-01 |  |  | OES Scoreboards | 2026-02-01
|  |  |  | 2026-02-01 |  |  | OES Scoreboards | 2026-02-01
Subtotal | Sum
Count
Verbal Commitment |  |  |  | 2026-03-01 | 2026-03-01 |  | LG Electronics | 2026-09-01
|  |  |  | 2026-01-15 | 2026-06-01 | 2027-10-01 | LG Electronics | 2027-09-01
|  |  |  | 2026-02-01 | 2026-06-01 |  | LG Electronics | 2026-09-01
|  |  |  | 2026-02-06 | 2/1/206 | 2026-03-30 |  | 2026-03-30
|  |  |  | 2026-01-16 | 3/1/206 | 2026-05-01 |  | 2026-04-10
|  |  |  | 2026-06-01 |  |  | Nitxeon | 2027-11-01
Subtotal | Sum |  |  |  | 2026-11-01
Count
Closed Won |  |  |  | 2024-12-20 |  |  | LG Electronics | 2026-07-18
|  |  |  | 2026-11-18 | 2026-03-01 | 2026-04-30 |  | 2026-04-30
|  |  |  | 2025-03-17 | 2026-03-15 | 2026-07-15 | LG Electronics | 2026-08-03
|  |  |  | 2025-12-01 | 2026-11-01 | 2027-02-01 | LG Electronics | 2027-01-01
|  |  |  | 2025-01-14 |  |  | Nitxeon | 2027-09-01
|  |  |  | 2025-12-15 | 2026-03-01 | 2026-03-26 | LG Electronics | 2026-03-01
|  |  |  | 2025-11-21 | 2026-03-01 | 2026-03-26 | LG Electronics | 2026-03-13
|  |  |  | 2026-01-01 |  |  |  | 2026-12-31
|  |  |  | 2025-02-12 |  |  | LG Electronics | 2025-08-01
|  |  |  | 2024-05-21 | 2026-03-15 | 2026-04-30 | LG Electronics | 2027-12-31
|  |  |  | 2025-12-18 | 2026-06-01 | 2027-06-01 | LG Electronics | 2027-04-01
|  |  |  | 2025-03-26 | 2026-07-06 | 2026-09-01 | Nitxeon | 2026-08-01
|  |  |  | 2025-12-01 | 2026-02-01 | 2026-03-19 | LG Electronics | 2026-03-20
|  |  |  | 2024-12-20 | 2026-01-05 | 2026-05-01 | LG Electronics | 2025-05-30
|  |  |  | 2025-09-17 |  |  | LG Electronics | 2026-04-01
|  |  |  | 2025-12-10 | 2026-01-18 | 2026-05-31 | LG Electronics | 2026-04-30
|  |  |  | 2025-10-31 | 2026-02-01 | 2026-04-01 | LG Electronics | 2026-03-31
|  |  |  | 2023-12-20 | 2026-03-01 | 2026-11-30 | LG Electronics | 2026-11-30
|  |  |  | 2025-11-03 | 2026-01-15 | 2026-05-11 | Dak | 2026-06-15
|  |  |  | 2025-05-07 | 2026-12-01 | 2026-02-04 | Dak | 2026-01-30
|  |  |  | 2025-10-31 | 2026-02-01 | 2026-03-15 | GoVision | 2026-02-02
|  |  |  | 2025-09-01 | 2026-04-01 | 2026-06-01 | LG Electronics | 2026-04-30
Subtotal | Sum
| Count | 22
Sum
| Count | 57
Sum
| Count | 57

## Ops
New Hires Requests |  | Parts Requests
Venue | Notes |  | Notes